- Prevention and Response to Sexual and Gender-Based Violence for Refugees, Asylum Seekers, and Host Communities in Egypt

- Terms of Reference

- Legal Awareness sessions for Refugees

- Cairo and Alexandria

- 2023

CARE Egypt Foundation (CEF):

Care Egypt Foundation for Development is a civil institution registered in the Central Administration of Associations at the Ministry of Social Solidarity with the number “833 for the year 2018” and its address is 25 Asmaa Fahmy Street - Fifth Floor ( Plot No. 1 - Square Y ) Qesm Nasr City 1st, Cairo, Egypt, and that the institution is subject to the provisions of the law regulating the practice of civil work No. 149 of 2019.

CARE Egypt Foundation for Development is building on the legacy and expertise of CARE International in Egypt since 1954, by designing, implementing and managing development programs and projects aimed at helping the neediest communities in Egypt, by building strategic partnerships with the government sector and the private sector, to help in meeting the basic needs and improving the quality and standard of life in a sustainable manner and consistent with the culture, reality and the local and national context.

The Foundation focuses its interventions and designs of its programs in the areas of economic and social empowerment of Egyptian women and girls, developing and improving the educational environment, supporting the agricultural sector, especially small farmers, improving government performance. As well as supporting capacity-building process among development partners through the application of different tools and methodologies for governance and social accountability, investing resources, and adopt initiatives that are in line with the foundation’s vision for the development and improvement of the living conditions of these communities and to address the root causes of poverty.

The Foundation is also committed to strengthening the role of the local civil society actors by including them as partners in all the foundation's projects to ensure building their capacity and enable them to play the developmental role required in the different development plans and programs.

The Foundation works on extracting international experiences in all areas of development, and presenting them in the local and national contexts.in addition to shedding the light and disseminate local experiences at the global level, in order to benefit from different global experiences and present the Egyptian development models to interested global actors.

Women’s Rights Program

The Women’s Rights (WR) Program is designed to empower underprivileged and marginalized women in Egypt who suffer from rights’ violation. The program’s goal is-by 2025-poor women in Egypt especially in Upper Egypt are empowered and enjoying a better quality of life, having attained their rights.

In order to achieve this goal, the program works with both the duty bearers in government and civil society, as well as rights bearers, women themselves, to address discriminatory attitudes and behavior towards women and girls.

The WR program works with the duty bearers to support their role to protect and uphold the rights of women, and also with the women to encourage them to understand voice and demand their rightful entitlements. The program works on three domains (agency, relations and structure) in order to empower poor women in Egypt to gain their rights. Through the focus on agency, women’s self-esteem and confidence are built, and women have increased financial independence to fulfill their potentials as productive and income-earning members of their households and society. We believe gender equality can be achieved when power relations within families are fair whilst tackling all forms of gender-based violence (GBV) within and outside the household, and structures like social norms or laws-particularly in the area of personal status, domestic violence- are reformed, passed and implemented fairly to everyone.

The program has three themes, which are:

1. Tackling Gender-based Violence (GBV).

2. Women’s Social and Economic Empowerment.

3. Engaging Men and Boys (EMB).

Prevention and Response to Sexual and Gender-Based Violence for Refugees, Asylum Seekers and Host Communities in Egypt Project

For 2023, CARE’s objective is to reduce and respond to GBV amongst refugee communities in Greater Cairo, Alexandria, and the North Coast, while enhancing the community-based approaches. This will be achieved through the following strategy: Addressing Gender Based Violence protection issues facing the targeted population through social-cultural and economic empowerment interventions.

1. Investing in gender equality & women’s empowerment.

2.Integration of women empowerment framework.

- Developing coordinated community response.

- Engaging key groups.

Objective of the Assignment:

The objective of this assignment is to deliver Legal awareness sessions to refugees to provide attendees with basic information on their rights, specifically focus on legal procedures regarding issuing legalized marriage licenses, divorce certificates, and birth certificates, as well as the legislation on sexual harassment, and legislation and reporting around cyber violence. Moreover, early marriage will be tackled from a legal perspective, especially in sessions that include male participants, as from CARE’s experience, it appears that fathers are often the ones who force their daughters into this harmful traditional practice.

After every session, pre- and post- evaluation surveys will be conducted, in order to evaluate whether attendees have gained knowledge on refugees’ legal rights, legal criminalization of early marriage, custody, and types of GBV. Sessions will be additionally followed by individual legal consultations to support survivors of GBV on a case-by-case basis.

Note:

Expected flexibility and availability to finish all sessions before the end of the task in December 2023. Consultants are expected to work in Cairo, Alexandria.

Cairo refers to Greater Cairo areas, and Alexandria could include delta and north coast governorates.

Scope of Work and Deliverables:

The consultant’s main deliverables are:

The consultant shall provide 13 Legal awareness sessions 8 at Cairo (6 for Female,2 for Male) and, 5 at Alexandria (3 for Female, 2 for Male) one-day sessions each one will be attended by 25 participants to reach in total 325 beneficiaries from refugees and asylum seekers Women and men in greater Cairo and Alexandria.

- The consultant shall provide a material with the content of the legal awareness sessions. Content must be appropriate for women and men. It should be discussed with the project’s team and get approved by CARE before conducting the sessions.

- The consultant shall provide pre and post surveys results and analysis measuring change in participants’ knowledge in the content delivered. Pre and post surveys should be approved by CARE before conducting the sessions.

- The consultant shall Provide 2 reports (15th of August and 15th of December 2023) documenting the process and results of the intervention. Reports must include individual and collective results of pre and post surveys conducted measuring the change in attendees’ knowledge on refugees’ legal rights, legal criminalization of child marriage, custody, and types of GBV.

- Kindly note that due to unstable COVID -19 pandemic situation, workshops might be fully or partially online if needed.

Consultant’s Duties and Responsibilities

1-Meeting with the project team to discuss and agree on the content of the sessions and refine the work plan before the execution of the assignment.

2-Develop and conduct Legal awareness sessions raising knowledge towards their legal rights, legal procedures in the host country and legal consequences of sexual harassment, early marriage and FGM.

3- Generate 2 detailed reports on assigned dates about conducted sessions.

4-Respect and ensure the privacy of all beneficiaries, and maintain a non-discriminatory attitude at all times regardless of ethnicity, religious beliefs, sexual orientation, and political affiliation.

5-Document successes and lessons learned as needed to be shared with the project team.

IMPORTANT NOTES:

-All deliverable must be in Arabic.

-The consultant submits a detailed technical and financial proposal for Alexandria, north coast and Cairo online and offline.

Consultant’s Qualifications:

- Knowledge and Expertise in the area of legal consultation preferably with refugees and displaced communities setting.

- A Minimum of a University Level Degree on law and Advanced knowledge and experience in the area of legal assistance for SGBV survivors, Development studies. An advanced degree will be an added advantage.

- Extensive knowledge and experience in the area of legal awareness sessions and Rights.

- Extensive Knowledge and experience in providing legal awareness sessions.

- Demonstrated experience in working with refugees.

- Demonstrated experience in dealing with different cultures and backgrounds.

- Demonstrated Knowledge and experience in gender issues and particularly SGBV.

Consultancy Level of Effort:

A total of 13 one-day Legal awareness sessions are foreseen for this assignment in addition to preparation and reporting.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | Time Frame |
| --- | --- | --- |
| Legal awareness sessions | -13 one-day Legal awareness sessions to reach a total of 325 beneficiaries: women and men divided on 8 sessions in greater Cairo, and 5 sessions in Alexandria based up on 25 attendees per session. - Reporting twice (15th of August and 15th of December, 2023). | June 2023 to December 2023 |

Assignment Time Frame:

Consultancy start and end date:   From June 2023 to December 2023.

Coordination and Reporting:

The Consultant will report on progress to the Project Manager who shall - within 7 working days of receipt - feed the Consultant back about the documents or reports received if they accept the reports or request amendments.

Technical and Financial Proposals:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be use in the assignment, including techniques and tools,

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time-frame.

- Financial Proposal:

The financial proposal should include a breakdown of the cost elements to clarify the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement.

Consultant Professional Service Fees- may be subject to taxation

| Description | Daily Rate in EGP | Number Days | Amount |
| --- | --- | --- | --- |

Consultant Administrative Costs – may not be subject to taxation

| Description | Unit Cost in EGP | Number Days | Amount |
| --- | --- | --- | --- |

Administrative Costs:  Such costs could include transportation, air tickets, lodging, per diem, departure taxes, training logistics, enumerators, interpreters, etc.  Note that per diem and lodging rates will be per CARE Egypt Foundation policy. No reimbursable expense in excess shall be incurred without CARE's prior written approval.  If Vendor travel reimbursement shall be made under this Agreement, then Vendor shall follow CARE's travel policies and be subject to CARE per diem rates.

The evaluation will be based on the following criteria according to the submitted documents:

| Evaluation type | Percentage |
| --- | --- |
| Qualifications | 10% |
| Service proposed (Methodology of work and expected results) | 30% |
| Experience (CV/ profile should be included) | 9% |
| Previous experience with CARE | 1% |
| Timeframe & commitment | 10% |
| Financial Evaluation | 40% |

P.S. applications rated less than 40% in the technical evaluation will be excluded.

Deadline for sending the technical and financial proposal is 24 July ,2023, Financial proposal should include Taxes and other expenses (if any), to be sent to CARE Egypt Foundation – Att. Nancy Rizkallah, Supply Chain Supervisor to (nancy.rezkallah@cef-eg.org), and (hady.farid@cef-eg.org) with subject (legal sessions at Greater Cairo, Alexandria 2023) / Prevention and Response to Sexual and Gender-Based Violence for Refugees, Asylum Seekers and Host Communities in Egypt . Any proposals received after the deadline mentioned, will not be considered. Thus, please ensure that the proposal should be received at CARE email inbox no later than 24 July, 2023.  Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Please feel free to contact us via email for any further details or inquiry via email prior 23 July ,2023)

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money.

CARE Egypt Foundation will respond to applicants with its decision within 5-7 working days from the proposal deadline.

CEF keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments should be made within 20 working days from invoice submission and linked with deliverables and timeline. No down payment (advance) is provided.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus, the financial proposal should include all taxes