Independent Verification Agent (IVA) in the World Bank Project, “Supporting Egypt Education Reform Project (P158809)”

- Terms of Reference

Technical Consultant

CARE Egypt Foundation (CEF):

Care Egypt Foundation for Development is a civil institution registered in the Central Administration of Associations at the Ministry of Social Solidarity with the number “833 for the year 2018” and its address is 5 Asmaa Fahmy Street - Fifth Floor ( Plot No. 1 - Square Y ) Qesm 1st Nasser City, Cairo, Egypt, and that the institution is subject to the provisions of the law regulating the practice of civil work No. 149 of 2019.

CARE Egypt Foundation for Development is building on the legacy and expertise of CARE International in Egypt since 1954, by designing, implementing and managing development programs and projects aimed at helping the neediest communities in Egypt, by building strategic partnerships with the government sector, the private sector and the private sector, to help in Meeting the basic needs and improving the quality and standard of life in a sustainable manner and consistent with the culture, reality and the local and national context.

The Foundation focuses its interventions and designs its programs in the areas of economic and social empowerment of Egyptian women, developing and improving the educational environment, supporting the agricultural sector, especially small farmers, improving government performance and supporting confidence-building processes among development partners through the application of tools and methodologies for governance and social accountability, through investing energies and ideas And adopt initiatives that are in line with the development and improvement of the economic and living conditions of these communities to deal with addressing the root causes of poverty.

The Foundation is also committed to strengthening the role of the local civil society by including it as a partner in all the Foundation's projects in a manner that ensures building its capabilities and enabling it to play the developmental role required in the government's sectoral and geographical development plans and programs.

The Foundation works on extracting the most important international experiences in all areas of development, and presenting them in the local and national contexts, in addition to working to shed light and disseminate local experiences at the global level, in order to benefit from global experiences and present Egyptian development models to interested and actors at the global level.

Education Program

The Education and Youth Empowerment Program aims to prepare youth and children for the future by ensuring they acquire the right knowledge, skills, and attitudes and that they find decent employment and break the cycle of poverty. In specific, the Education and Youth Empowerment program posits that poor and marginalized children and youth in Egypt, aged 6 to 29, do not enjoy their social and economic rights. Accordingly, the program’s objectives have been designed to address and provide remedies for children and youth’s deprivation from social and economic rights.

Independent Verification Agent (IVA) in the World Bank Project

The Ministry of Education and Technical Education (MoETE) requested World Bank support to strengthen the reform of the system through EDU 1.0 (Current Education system) and provide an enabling environment to catalyze EDU 2.0 (New education system). The WB-financed Project will support MoETE education reform program (2018-2030) over a five-year implementation period (2018-2025) to strengthen the reform of the current education system and intends to apply part of the proceeds for consulting services. The Project Coordination Unit (PCU), Ministry of Education and Technical Education (MoETE) contracted Care Egypt Foundation, as an Independent Verification Agent (IVA). CARE will prepare periodic and annual Results Verification Reports that will be simultaneously submitted to the PCU and the World Bank to guide the disbursement amount of the loan. CARE Egypt Foundation has been commissioned to verify results achievement, in accordance with the agreed methodology, as laid out in a Verification Protocol matrix and have been physically delivered, in an approved manner, and properly documented. Results will be verified through administrative records and documents, independent verification, through consultations and spot checks with implementation agencies. to confirm the submitted data and test the accuracy of results claimed. CARE will undertake the following tasks: • Carry out the following verification work: a. Review of Documents and Records: CARE experts will review the availability and completeness of required action plans, research, and strategy documents for the verification of different DLR targets, as applicable. b. Verify that results have been completed and have received the required endorsements and approvals as per agreed protocols in each stage. • Prepare a results verification report based on the evidence received from the different sources of DLR-related information and integrated by the MoETE.

Objective of the Assignment:

Collaborate with Care team to ensure the verification of data as per project agreement.

Scope of Work and Deliverables:

- Develop the IVA verification Plan for the DLRs included in the table below.

- Develop tools for data collection including Interview guides as well as phone surveys as needed and train team members as needed on using them.

- Attend planning meetings with the PCU and World Bank as needed.

- Writing the verification report and integrating comments from the PCU and World Banks as needed.

- Train DME officer on basic data visualization tools.

- Review DME officer’s work and provide feedback when necessary.

Consultant’s Qualifications:

• Experience in data analysis and report writing.

• Excellent command of English and Arabic skills.

• Individual and group work capabilities.

• Previous experience in working with data specifically with an NGO.

Consultancy Level of Effort

A total of (20) working days is foreseen for this assignment including preparation and reports.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | No. Days/ Time Frame |
| --- | --- | --- |
| 2.1 | DLR Verification | 7.75 |
| 2.2a | DLR Verification | 2 |
| 7.2c | DLR Verification | 8.75 |
| 11.4a/b | DLR Verification | 1.5 |
| Total |  | 20 |

Execution of Assignment:

Consultancy start and end date:   From 1/7/2023  to    30 /9/2023

Assignment location:-

Remote

Coordination and Reporting:

The Consultant will report on progress to  (Lillian Farouk/Education Program Director) who shall within 7 working days of receipt notify the Consultant of its decision concerning the documents or reports received, giving reasons should s/he reject the reports or documents, or request amendments.

Conditions of Implementation:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be use in the assignment, including techniques and tools,

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time-frame.

- Financial Proposal:

The financial proposal should include a taxes and breakdown of the cost elements to assist in determining the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement

Consultant Professional Service Fees- may be subject to taxation

| Description | Daily Rate in EGP | Number Days | Amount |
| --- | --- | --- | --- |
| Technical Consultant Fees | 4,700 | 20 | 94,000 |

Deadline for sending the technical and financial proposal is ______31/10/2023__________, Financial proposal should include Taxes and other expenses (if any), to be sent to CARE Egypt Foundation –

* Any proposals received after the deadline mentioned, will not be considered. Thus, please ensure that the proposal should be received at CARE email inbox no later than _____________31/10/2023______.  Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Please feel free to contact us via email for any further details or inquiry via email prior (__31/10/2023)

(2 pm)

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money.

CARE Egypt Foundation will respond to applicants with its decision within 5-7  working days from the proposal deadline.

CEF keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments (done within 20 working days from invoice submission and linked with deliverables and timeline. No down payment (advance) is provided.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus the financial proposal should include all taxes