Comprehensive approach to eliminate Harmful practices in Upper Egypt – UNFPA Project

- Terms of Reference

Y-PEER Training of Trainers

CARE Egypt Foundation (CEF):

Care Misr Foundation for Development is a civil institution registered in the Central Administration of Associations at the Ministry of Social Solidarity with the number “833 for the year 2018” and its address is 5 Asmaa Fahmy Street - Fifth Floor ( Plot No. 1 - Square Y ) Qesm 1st Nasser City, Cairo, Egypt, and that the institution is subject to the provisions of the law regulating the practice of civil work No. 149 of 2019.

CARE Egypt Foundation for Development is building on the legacy and expertise of CARE International in Egypt since 1954, by designing, implementing and managing development programs and projects aimed at helping the neediest communities in Egypt, by building strategic partnerships with the government sector, the private sector and the private sector, to help in Meeting the basic needs and improving the quality and standard of life in a sustainable manner and consistent with the culture, reality and the local and national context.

The Foundation focuses its interventions and designs its programs in the areas of economic and social empowerment of Egyptian women, developing and improving the educational environment, supporting the agricultural sector, especially small farmers, improving government performance and supporting confidence-building processes among development partners through the application of tools and methodologies for governance and social accountability, through investing energies and ideas And adopt initiatives that are in line with the development and improvement of the economic and living conditions of these communities to deal with addressing the root causes of poverty.

The Foundation is also committed to strengthening the role of the local civil society by including it as a partner in all the Foundation's projects in a manner that ensures building its capabilities and enabling it to play the developmental role required in the government's sectoral and geographical development plans and programs.

The Foundation works on extracting the most important international experiences in all areas of development, and presenting them in the local and national contexts, in addition to working to shed light and disseminate local experiences at the global level, in order to benefit from global experiences and present Egyptian development models to interested and actors at the global level.

Women’s Rights Program

The Women’s Rights (WR) Program is designed to empower poor and marginalized women in Egypt who suffer from rights’ violation. Its impact goal is: By 2025, poor women in Egypt especially in Upper Egypt are empowered and enjoying a better quality of life, having attained their rights. In order to achieve this goal, the program works with both the duty bearers in government and civil society, as well as rights bearers, women themselves, to address discriminatory attitudes and behavior towards women and girls.

The WR program works with the duty bearers to support their role to protect and uphold the rights of women, and also with the women to encourage them to understand voice and demand their rightful entitlements. The program works on three domains (agency, relations and structure) in order to empower poor women in Egypt to gain their rights. Through the focus on agency, women’s self-esteem and confidence are built, and women have increased financial independence to fulfill their potential as productive and income-earning members of their households and society. In addition, when power relations (families) are gender sensitive whilst tackling all forms of gender-based violence (GBV) within and outside the household, and when structures (social norms or laws) particularly in the area of personal status, domestic violence are reformed, passed and implemented, gender equality can be achieved.

The program has three themes, which are:

1. Tackling Gender-based Violence (GBV).

2. Women’s Social and Economic Empowerment.

3. Engaging Men and Boys (EMB).

Project: Comprehensive approach to eliminate Harmful practices in Upper Egypt - UNFPA Project

Background

The Women’The women Rights Program is designed to empower poor and marginalized women in Egypt who suffer from rights’ violation. Its impact goal is: By 2025, poor women in Egypt especially in Upper Egypt are empowered and enjoying a better quality of life, having attained their rights. In order to achieve this goal, the program works with both the duty bearers in government and civil society, as well as rights bearers, women themselves, to address discriminatory attitudes and behavior towards women and girls.

One of the main issues women face as gender-based violence is domestic violence, however, harmful practices still widely prevail within the society’s traditions. Female Genital Mutilation (FGM) and early marriage practices/crimes.

CARE Egypt has been selected by UNFPA to implement a project addressing Gender Based Violence against women in Upper Egypt. This project works towards ending FGM and early marriage, and supporting survivors who experienced any types of violence, exploitation, or abuse in the areas of Assiut, Sohag, Menya and Beni Suef.

The project will contribute to the long-term impact of ''women and girls in target communities fully enjoy their lives free of the risk of FGM and early marriage’’. It seeks to address the root causes of FGM and early marriage, develop a set of interventions targeting various stakeholders. These interventions aim to raise community awareness on reproductive health and girls’ education, actively engage men and boys in the discussion against early marriage, equip a cadre of local volunteers with the knowledge and skills needed to actively participate in the efforts to reduce the prevalence of harm practices and finally, networking all efforts in organized advocacy campaigns capable to achieve more gains that give women and girls a safe environment free from harmful practices in the targeted governorates.

Upon the partnership between CARE Egypt, UNFPA and Y-PEER Egypt to empower young people’s agency to make informed decisions regarding their Sexual and Reproductive health and Family Planning also promoting healthy lifestyle through peer-to-peer approach.

The activities for SRHR education, and Family planning through comprehensive information, among young people as stipulated in the project are to be held through Y-PEER Egypt members in collaboration with CARE Egypt and supported by UNFPA Egypt.

Objective of the Assignment:

Y-PEER TOTs are designed to build the capacity of Y-PEER for further cascading peer education trainings and awareness sessions in 26 different governorates on SRH, FP and GBV integrating interactive techniques, sports for development and theatre-based techniques with utilization of online tools.

By the end of these trainings, it is expected that participants will have knowledge, skills, and techniques to deliver the following:

- A comprehensive understanding of SRH, family planning and GBV concepts, principles and components using peer to peer approach.

- Acquisition of detailed information on SRH, FP and GBV topics including safe motherhood, child marriage, FGM, contraceptives, and other related topics.

- Acquiring essential skills to be able to deliver knowledge interactively and through interactive theatre techniques and sports techniques.

- Get updated about SRH, FP and GBV situation and statistics in Egypt.

- Full understanding of peer education methodology, approaches and related theories.

- Agenda development and training design with practical application.

- Understand the difference between raising awareness and interrelated terms as advocacy and counselling.

- Updates about SDGs and 2030 strategy and challenges facing goals related to SRH, FP, GBV and population issues in Egypt.

- Essential knowledge and skills regarding training and facilitation related models and their utilization into action.

- Acquire advanced knowledge on trends related to SRH and FP.

Scope of Work and Deliverables:

The consultancy is open for a team of trainers (3 to 4 trainers) they will be responsible for designing, implementing, and reporting of 3 TOTs (6 days each) on utilization of peer education methodology using interactive techniques, theatre-based techniques, and sports for development.

- 3 TOTs with total of 18 training days 6 days each (8 to 10 hours per day), 2 days for preparing and 2 days for finalizing documents including training reports this means the total working days will be 22 days.

- Detailed training agenda, pre & post-tests, training materials (manuals, handouts, Power point presentation…. etc.) to be sent before the training.

- 3 Training reports to be submitted with maximum of 5 days after the training including pre/post-test results, and final trainees’ evaluation.

Training Timeline and location:

- The training will take place in Cairo within the period between (20 November 2023 – 8 December 2023)

- CARE Egypt will cover all the accommodation, daily meals, break and transportation to all trainers and trainees.

Consultant’s Qualifications:

- At least 6 years’ training experience in SRH and GBV issues.

- Concrete knowledge on SRH, FP and GBV issues.

- Experience in conducting TOTs with CSOs or NGOs considered mandatory.

- Having at least one trainer certified as an International Y-PEER trainer is a must.

- Ability to develop and implement post training follow-up and evaluation module for CSOs and NGOs training participants is a plus.

- Ability to collaborate with CARE Egypt and project partners to providing mentoring support during and after the training.

Consultancy Level of Effort

3 TOTs with total of 18 training days 6 days each (8 to 10 hours per day), 2 preparation days and 2 days for finalizing documents including training reports this means the total working days will be 22 days.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | No. Days/ Time Frame |
| --- | --- | --- |
| Preparation | Preparing the training materials | Up to 2 days |
| Implementation | 90 Y-PEER educators and trainers capacitated on: - RH and FP with utilization of interactive techniques as Sports and theatre | 18 days |
| Reporting | 3 final Reports | 2 days |

Execution of Assignment and deliverables:

Training requirements

- Training materials: agenda, PPT, content etc

- 3 TOTs with total of 18 training days 6 days each in November and December 2023

- 3 Final training reports including pre and post analysis and trainees evaluation

Coordination and Reporting:

The Consultant will report on the detailed training and activities presented.

Conditions of Implementation:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be use in the assignment, including techniques and tools,

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time-frame.

- Financial Proposal:

The financial proposal should include a breakdown of the cost elements to assist in determining the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement

Consultant Professional Service Fees- may be subject to taxation

| Description | Daily Rate in EGP | Number Days | Amount |
| --- | --- | --- | --- |

Consultant Administrative Costs – may not be subject to taxation

| Description | Unit Cost in EGP | Number Days | Amount |
| --- | --- | --- | --- |

Administrative Costs:  Such costs could include transportation, air tickets, lodging, per diem, departure taxes, training logistics, enumerators, interpreters, etc.  Note that per diem and lodging rates will be per CARE Egypt Foundation policy. No reimbursable expense in excess of _________ [Amount] (currency___) shall be incurred without CARE's prior written approval.  If Vendor travel reimbursement shall be made under this Agreement, then Vendor shall follow CARE's travel policies and be subject to CARE per diem rates.

The evaluation will be based on the following criteria according to the submitted documents:

| Evaluation type | Percentage |
| --- | --- |
| Qualifications | 10% |
| Service proposed (Methodology of work and expected results) | 30% |
| Experience (CV/ profile should be included) | 9% |
| Previous experience with CARE | 1% |
| Timeframe & commitment | 10% |
| Financial Evaluation | 40% |

P.S. applications rated less than 40% in the technical evaluation will be excluded.

Deadline for sending the technical and financial proposal is 31 October  2023 Financial proposal should include Taxes and other expenses (if any), to be sent to CARE Egypt Foundation – Att. Hady Farid, Procurement Officer to (hady.farid@cef-eg.org ), with subject  (Y-PEER TOTs)  * Any proposals received after the deadline mentioned, will not be considered. Thus, please ensure that the proposal should be received at CARE email inbox no later than 31 October 2023  (11:59pm).  Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Please feel free to contact us via email for any further details or inquiry via email prior (31 October 2023)

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money.

CARE Egypt Foundation will respond to applicants with its decision within 5-7 working days from the proposal deadline.

CEF keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments (done within 20 working days from invoice submission and linked with deliverables and timeline. No down payment (advance) is provided.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus the financial proposal should include all taxes

Note: The electronic invoice is must