Protection response for Sudanese Refugees in Egypt

- Terms of Reference

- Psychosocial awareness sessions & psychosocial groups

- For Sudanese in Cairo 2024

CARE Egypt Foundation (CEF):

CARE Egypt Foundation for Development, registration no 833 for the year 2018 at the Ministry Of Social Solidarity in Egypt. CARE Egypt Foundation (CEF) is an Egyptian, non-governmental organization harnessing the legacy of CARE International in Egypt since 1954 to fight poverty and improve livelihoods. We envision Egypt as a place where everyone enjoys economic opportunities, equality and social justice. We empower women and girls by sharing our values amongst the private sector, government and civil society.

Women’s Rights Program

The Women’s Rights (WR) Program is designed to empower poor and marginalized women in Egypt who suffer from rights’ violation. Its impact goal is: By 2025, poor women in Egypt especially in Upper Egypt are empowered and enjoying a better quality of life, having attained their rights. In order to achieve this goal, the program works with both the duty bearers in government and civil society, as well as rights bearers, women themselves, to address discriminatory attitudes and behavior towards women and girls.

The WR program works with the duty bearers to support their role to protect and uphold the rights of women, and also with the women to encourage them to understand voice and demand their rightful entitlements. The program works on three domains (agency, relations and structure) in order to empower poor women in Egypt to gain their rights. Through the focus on agency, women’s self-esteem and confidence are built, and women have increased financial independence to fulfill their potential as productive and income-earning members of their households and society. In addition, when power relations (families) are gender sensitive whilst tackling all forms of gender-based violence (GBV) within and outside the household, and when structures (social norms or laws) particularly in the area of personal status, domestic violence are reformed, passed and implemented, gender equality can be achieved.

The program goal:

To implement and strengthen prevention and response mechanisms for Sudanese refugees arriving in Alexandria, Aswan and Cairo by adopting a combination of rights-based, survivor-centred, and community development approaches.

To enhance psychosocial well-being and resilience among Sudanese refugees.

Objective of the Assignment:

The objective of this assignment is two-fold:

- The consultant will conduct several psychosocial informative sessions around sexual and gender based violence (SGBV), its definition, forms, effects, and treatment using a psychosocial approach to reach in total 120 Sudanese women through 6-8 awareness sessions conducted in with 20 participants. The sessions should also cover types of SGBV, trauma and PTSD, resiliency, a sense of isolation, emotional awareness, as well as managing emotions, anger, and memories. When addressing SGBV and child protection issues, there is a need for building long-term relations with the community. Through these sessions women will know and understand SGBV, child protection causes and effects, and will be aware of available services. After every session, pre- and post- evaluation surveys will be conducted in order to evaluate whether attendees have gained the desired knowledge.

- The consultant will identify SGBV survivors from the psychosocial informative sessions and from the individual counseling sessions conducted in need of psychosocial support in a group setting to reach in total 80 beneficiaries through conducting 4 psychosocial support groups each group for two-day workshop, each group with target of 15-20 participants. Professional psychiatrists and counselors are requested to facilitate psychosocial support in a group setting. The therapy group should be much like a safe place in which members gain a sense of belonging and acceptance, they share feelings and experiences which help them relieve pain, guilt and stress. Members should be able to share their strengths and help others in the group, which can boost self-esteem and confidence. By interacting with other people and receiving feedback from the group and the therapist, each individual can gain a greater understanding of himself or herself, explore how childhood experiences contributed to personality and behaviors. They can also learn to avoid behaviors that are destructive or unhelpful for them. Studies have shown that group therapy can be an effective treatment choice for depression and traumatic stress. In each session, a presentation on a specific topic will be conducted followed by small sharing groups where each participant will get the chance to share concerns among the group. Small groups are to be organized with two facilitators to ensure a peaceful session. Participants will agree on the rules of the group sessions such as respecting confidentiality, committing to attend all sessions, and reserving judgment.

Scope of Work and Deliverables:

The consultant’s main deliverables are:

1- Psychosocial Informative sessions:

a. The consultant shall provide psychosocial informative sessions with a focus on SGBV to reach in total 120 beneficiaries.

b. The consultant shall provide a document with the content of the informative sessions. Content should be approved by CARE before conducting the sessions.

c. The consultant shall provide pre and post surveys measuring change in participants’ knowledge in the content delivered. Pre and post surveys should be approved by CARE before conducting the sessions. Analysis of the pre and post surveys will be done by the consultant and shared with CARE for reviewing and confirming.

d. The consultant shall provide handouts to participants containing information to supplement the sessions. Handouts must be approved by CARE before conducting the sessions.

e. Generate reports on each session conducted. Reports must include individual and collective results of pre and post surveys conducted, measuring the change in attendees’ knowledge in regards to SGBV.

2- Psychosocial support groups:

a. The consultant shall provide 4 psychosocial support groups to reach in total 80 beneficiaries.

b. The consultant shall provide pre and post surveys measuring change in participants’ wellbeing. Pre and post surveys should be approved by CARE before conducting the psychosocial support groups.

c. Generate reports on each session conducted. Reports must include individual and collective results of pre and post surveys conducted, measuring the change in attendees’ psychosocial wellbeing.

Duties and Responsibilities

- Meet with the project’s team to discuss and agree on the content of the sessions and refine the work plan for the execution of the assignment.

- Design and implement of psychosocial informative sessions with a focus on SGBV to reach 120 beneficiaries.

- Identify cases, based on set criteria, from participants in the informative sessions or individual counseling in need of psychosocial support in a group setting.

- Form 4 groups of 20 participants each with similar needs to participate in psychosocial support in a group setting.

- Generate monthly reports and case studies on informative sessions, group therapy and individual sessions. Reports must include results of pre and post surveys to highlight progress.

- Document successes and lessons learned.

- Highlight successful implementation tools that have been used and proved impactful for further scale up.

- Attend a monthly meeting with CARE Case Management Supervisors, Project Manager and M&E unit.

- Respect and ensure the confidentiality of all beneficiaries, and maintain a non-discriminatory attitude at all times regardless of ethnicity, religious beliefs, sexual orientation, and political affiliation. As well as code of conduct and professional therapeutic relations.

- Vendor’s time sheet

- Beneficiaries’ attendance

- Approved final report with no details (due to confidentiality) to confirm that the services is done.

Consultant’s Qualifications:

Knowledge and Expertise in the area of Counseling, psychological support and gender:

❑ Extensive knowledge and experience in the area of counseling, psychological support and support groups.

❑ Extensive knowledge of gender issues and SGBV.

❑ Demonstrated experience in counseling and consultation on issues related to SGBV including sexual abuse.

❑ Extensive Knowledge and experience in providing SGBV and psychosocial awareness sessions.

❑ Demonstrated experience in working with refugees.

❑ Demonstrated experience in dealing with different cultures and backgrounds. Training and Education:

❑ Experience in designing and delivering training and awareness sessions to different groups

❑ Experience in implementing awareness sessions employing adult education tools and techniques

❑ Capacity to use different educational tools employing case studies, role playing, audio/visuals, presentations, discussions and facilitating groups.

❑ Ability to lead discussions and arguments around sensitive and controversial topics.

Consultancy Level of Effort

- A total of 6 working days is foreseen for the awareness sessions including preparation and reports.

- A total of 32 working days is foreseen for the support groups including preparation and reports.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | No. Days/ Time Frame |
| --- | --- | --- |
| Psychosocial informative sessions | - psychosocial approach to reach in total 120 beneficiaries (4 groups) - Reports submitted with pre and post survey results | January 2024 to Sept 2024 |
| Psychosocial support groups | - 4 groups formed - 80 participants. Each with 20 participants (6:8 sessions per group) - Reports submitted with pre and post survey results | Jan. - Sept 2024 |

Execution of Assignment: Consultancy start and end date:

Psychosocial informative sessions: from Jan. 2024 to Sept 2024

Psychosocial support groups: from Jan. 2024 to end of Sept 2024

Coordination and Reporting:

The Consultant will report on progress to the Field supervisor who shall within 7 working days of the receipt notify the Consultant of its decision concerning the documents or reports received, giving reasons should s/he reject the reports or documents, or request amendments.

Conditions of Implementation:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be used in the assignment, including techniques and tools,

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time frame.

- Financial Proposal:

The financial proposal should include a breakdown of the cost elements to assist in determining the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement

Consultant Professional Service Fees- may be subject to taxation

| Description | Daily Rate in EGP | Number Days | Amount |
| --- | --- | --- | --- |
| Preparation |  |  |  |
| Workshop/session/group |  |  |  |
| Reports |  |  |  |

Consultant Administrative Costs – may not be subject to taxation

| Description | Unit Cost in EGP | Number Days | Amount |
| --- | --- | --- | --- |
| Transportation |  |  |  |

Administrative Costs:  Such costs could include transportation, air tickets, lodging, per diem, departure taxes, training logistics, enumerators, interpreters, etc.  Note that per diem and lodging rates will be per CARE Egypt Foundation policy. No reimbursable expense in excess of _________ [Amount] (currency___) shall be incurred without CARE's prior written approval.  If Vendor travel reimbursement shall be made under this Agreement, then Vendor shall follow CARE's travel policies and be subject to CARE per diem rates.

The evaluation will be based on the following criteria according to the submitted documents:

| Evaluation type | Percentage |
| --- | --- |
| Qualifications | 10% |
| Service proposed (Methodology of work and expected results) | 30% |
| Experience (CV/ profile should be included) | 9% |
| Previous experience with CARE | 1% |
| Timeframe & commitment | 10% |
| Financial Evaluation | 40% |

P.S. applications rated less than 40% in the technical evaluation will be excluded.

Deadline for sending the technical and financial proposal is __20 January 2024

Financial proposal should include Taxes and other expenses (if any), to be sent to CARE Egypt Foundation – Att. Hady Farid, Procurement Officer to ( Hady.Farid@cef-eg.org ), with subject (pls. insert the TOR name/ project)  * Any proposals received after the deadline mentioned, will not be considered. Thus, please ensure that the proposal should be received at CARE email inbox no later than _________________ (11:59pm).  Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money.

CARE Egypt Foundation will respond to applicants with its decision within 5-7 working days from the proposal deadline.

CEF keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments (done within 20 working days from invoice submission and linked with deliverables and timeline. No down payment (advance) is provided.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus the financial proposal should include all taxes and abide to submit electronic invoices.