ILO Social Enterprise

- Terms of Reference

Final Evaluation

CARE Egypt Foundation (CEF):

Care Egypt Foundation for Development is a civil institution registered in the Central Administration of Associations at the Ministry of Social Solidarity with the number “833 for the year 2018” and its address is 5 Asmaa Fahmy Street - Fifth Floor ( Plot No. 1 - Square Y ) Qesm 1st Nasser City, Cairo, Egypt, and that the institution is subject to the provisions of the law regulating the practice of civil work No. 149 of 2019.

CARE Egypt Foundation for Development is building on the legacy and expertise of CARE International in Egypt since 1954, by designing, implementing and managing development programs and projects aimed at helping the neediest communities in Egypt, by building strategic partnerships with the government sector, the private sector and the private sector, to help in Meeting the basic needs and improving the quality and standard of life in a sustainable manner and consistent with the culture, reality and the local and national context.

The Foundation focuses its interventions and designs its programs in the areas of economic and social empowerment of Egyptian women, developing and improving the educational environment, supporting the agricultural sector, especially small farmers, improving government performance and supporting confidence-building processes among development partners through the application of tools and methodologies for governance and social accountability, through investing energies and ideas And adopt initiatives that are in line with the development and improvement of the economic and living conditions of these communities to deal with addressing the root causes of poverty.

The Foundation is also committed to strengthening the role of the local civil society by including it as a partner in all the Foundation's projects in a manner that ensures building its capabilities and enabling it to play the developmental role required in the governments sectoral and geographical development plans and programs.

The Foundation works on extracting the most important international experiences in all areas of development, and presenting them in the local and national contexts, in addition to working to shed light and disseminate local experiences at the global level, in order to benefit from global experiences and present Egyptian development models to interested and actors at the global level.

Education Program

The objective of the Education program is to create opportunities for children, living in poverty in Egypt from 6-18 years, to enjoy their right to quality education and become empowered citizens in their communities with increased opportunities to realize their full potential and rights.

Barriers preventing the realization of this objective are many and are multi-faceted. Thus, the program adopts a multi-dimensional strategy that aims to tackle a multitude of factors contributing to the weakening of educational services in Egypt. It is believed that when improved household incomes, increased students’ exercise of leadership in households and communities, and access of all children to quality basic education opportunities are achieved together; simultaneously with changed norms, attitudes and behavior and effective policy regulation; the program objective will be achieved.

The program seeks to directly influence the quality of education provided by the schools through building the capacity of school staff (teachers, social workers, school administration, etc.), activating structures/mechanisms (board of trustees, student unions, teacher training units, child protection committees, etc.) that can guarantee sustainability of the interventions, improving the physical environment of schools (through renovation), engaging the community and other stakeholders in education (local NGOs, government partners, etc.), and supporting policy-makers in replicating successful models across the nation along with advocacy for policy change when relevant.

Project Brief:

Social entrepreneurship is an emerging phenomenon, defined as organizations seeking business solutions to social problems. Care Egypt with ILO aims to promote social entrepreneurship as a driver for social change, enabling target groups to transform social business ideas into sustainable enterprises.

Project objectives:

### Objective: Social entrepreneurship promoted in local communities (Target groups outreach and selection)

Activity 1.1: Build awareness of target groups on social enterprises concept, and to promote social entrepreneurship to the broader community.

- Activity 1.1.1: Conduct awareness social media campaign webinars and Facebook posts

  - Description: Conducting 6 webinars by Guest Speakers (once each month) to reach 3000 participants (at least 500 per webinar) about social enterprises concept, and promote social entrepreneurship to the broader community in the covered governorates. Also post 9 Facebook posts/short videos on social media channels with a funded advertising campaign.

- Activity 1.1.2: Conduct an event to meet stakeholders for 1 day in a round table

  - Description: Participate and invite stakeholders to an event.

- Activity 1.1.3: Offline outreach (participate in 3 events, university visits, youth centers, ICT clubs)

  - Description: Participate in 3 events to target 1500 participants (500 per event) through university visits and youth centers. Graduates and refugees will be reached through WFS and LHs.

Activity 1.2: Select youth champions in target areas for the SYBSE trainings

- Activity 1.2.1: Identify through the online applications the most youth champions who meet the criteria.

  - Description: After beneficiaries fill out an online application, the applicants will be initially screened by CARE Egypt. Those who pass the initial screening will be interviewed by ILO certified trainers for the final selection. Interviews will be one-on-one online interviews prior to the trainings. The purpose is to identify existing knowledge, skills, and learning needs.

- Activity 1.2.2: Selection of youth who will attend SYBSE trainings based on clear criteria through interviews, and training needs analysis.

### Objective: Entrepreneurs developed their entrepreneurial skills and social enterprises formulated and established (Enterprise development trainings)

Activity 2.1: Implement SYBSE training

- Activity 2.1.1: Implementing the Toe workshop for the SYBSE package demanded by the participants

  - Description: The 5 days training will be carried out by trainers accredited by the International Labor Organization for 1000 applicants. Each training is implemented by 2 ILO Certified trainers in 8 batches in the target governorates, 6 groups per batch (total 42 groups) using certified ILO curriculums.

### Objective: Business running successfully (Business development support and post-training support)

Activity 3.1: Needs Assessment

- Activity 3.1.1: Business Plan Analysis

  - Description: The needs assessment pillar will commence with an analysis of the business plans extracted from the trainings by the technical advisor on CARE Egypt’s team to determine the specific support individual and grouped beneficiaries might need. This will help create clusters from the beneficiary’s pool.

- Activity 3.1.2: Clustering

- Activity 3.1.3: Coaching and mentorship on business plans

  - Description: Assist the beneficiaries to prepare a business plan and evaluate its viability each trainer has to coach 10 beneficiaries (unclustered)/2 groups (clustered) for 3 hours each, total of 20 days.

- Activity 3.1.4: Survey 1 (Online Community)

  - Description: Prior to designing and availing specific post-training support activities, a survey will be distributed among the beneficiaries to identify their top three areas in which they need support to disseminate material online.

- Activity 3.1.5: Survey 2

  - Description: Prior to designing and availing specific post-training support activities, a survey will be distributed among the beneficiaries to identify their top three areas in which they need support (legal advice, financial planning, accessing exhibitions, marketing, etc.)

Activity 3.2: Community Building

- Activity 3.2.1: Entrepreneurs' Online Community

  - Description: Build a community online that will connect the beneficiaries with each other for knowledge sharing and mutual support. This community is based on the idea that gave birth to the social enterprise.

Activity 3.3: Resource Mapping

- Activity 3.3.1: Consolidate available material and upload it on the entrepreneur online community such as legal or other related topics.

  - Description: Conduct a resource mapping activity to determine what resources and materials already exist that can be consolidated and availed to the beneficiaries through the online community such as legal or other related topics.

- Activity 3.3.2: Determine Gaps

  - Description: Based on the materials available and the materials missing, workshops will be designed to address the determined gaps. This activity is necessary to ensure that the supporting activities that follow address the gap and the aspects missing and avoid replication of material and knowledge.

Scope of work:

Below is the list of Main indicators intended to be measured by the final evaluation

### Global indictor:
1)- # and % of disaster/crisis-affected people supported through/by CARE who recovered household goods, assets and/or income opportunities

2)-% of disaster/crisis affected people in areas of CARE responses who report satisfaction with regards to relevance, timeliness and accountability of humanitarian interventions.

3)-# and % of women who have increased capability to participate equitably in economic activities

Consultant’s Qualifications:

Technical Requirements

- Strong knowledge of Entrepreneurship, the education sector, and monitoring and evaluation tools.

- Master’s Degree (or equivalent experience) in international development field and/or research fields

- Working experience with international organizations

- Demonstrated writing and oral communication skills

- Ability to establish priorities in a time-sensitive environment, and meet deadlines with strong attention to detail and quality

- Specific expertise in research and monitoring and evaluation in Egypt

Core Competencies

- People Skills: Ability to work independently and as a team player who demonstrates leadership skills.

- Communication Skills: Well developed written and oral communication skills. Able to communicate clearly and sensitively with internal and external stakeholders as a representative of CARE. This includes effective negotiation and representation skills.

- Integrity: Works with trustworthiness and integrity and has a clear commitment to CARE's core values and humanitarian principles.

- Resilience/Adaptability and flexibility: Ability to operate effectively under extreme circumstances including stress, high security risks and harsh living conditions. Works and lives with a flexible, adaptable and resilient manner.

- Awareness and sensitivity of self and others: Demonstrates awareness and sensitivity to gender and diversity. Have experience and the ability to live and work in diverse cultural contexts in a culturally appropriate manner. Has a capacity to make accurate self-assessment particularly in high stress and high security contexts.

- Work style: Is well planned and organized even within a fluid working environment and has a capacity for initiative and decision making with competent analytical and problem-solving skills.

- Knowledge and skills: knowledge of CARE policies and procedures, Sphere and the Red Cross/ NGO Code of Conduct. Requires general finance, administration, information management and telecommunication skills and proficiency in information technology/ computer skills.

Consultancy Level of Effort

A total of (5) working days is foreseen for this assignment including preparation and reports.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | No. Days/ Time Frame |
| --- | --- | --- |

Methodology:

The consultant will be requested to use a mixed-methods approach in addressing aforementioned questions. Additionally, research tools will be designed and selected with the project team. All questions will reflect indicators in the project’s M&E system. These indicators, which all have proposed tools and means of verification for measurement are gender sensitive and disaggregated by gender, nationality, age and location.

Upon starting the assignment, the Consultant will receive all M&E documents to the project (logical framework, M&E plan, etc.), as well as the project description document.

Objective of the Assignment:

CARE Egypt is seeking the services of a professional consultant in the field of monitoring and evaluation for an assignment with the objective of conducting final evaluation study for the project. This study will act as a guiding document to all M&E activities for the rest of the project and will be a reference document as to which any further analyses will be compared.

Main Objectives of the Final Evaluation:

- Assess the internal and external factors that may affect the project in addition to the global indicator.

- To generate recommendations to be used while implementing similar activities in the future

- To measure the evaluation criteria and the values of the indicators placed for the project’s overall objective

Deliverables:

- Meet with the project’s Manager, and the monitoring and evaluation officer to further discuss and agree on the methodology and approach proposed by the evaluator in his/her proposal, collect needed information on the project, and set a time plan including milestones and reporting management with the consultant.

- Review the project’s documents including the proposal and the logical framework;

- Implement thorough desk review and combine analytically all the gathered information, and submit a work plan.

- Develop data collection tools. Tools will be reviewed and must be approved by CARE before fieldwork.

- Plan and coordinate field visits with the assistance of the project team for applying the tools and meeting with relevant recipients

- Inception Report: The inception report will be delivered to CARE after the initial meeting and desk review have taken place. The report should include the objectives of the evaluation, a detailed plan of how the evaluation will be carried out describing research methodology, qualitative and quantitative survey, proposed guiding questions for semi-structured interviews, focus group discussion or other approaches, and proposing the draft data collection questionnaires. The inception report should also provide a clear matrix of roles and responsibilities indicating the persons involved in the evaluation and their roles, the key internal and external stakeholders to be involved, a detailed work plan and timeline including the number of days and persons involved. It should also summarize the preliminary findings and any preliminary hypotheses resulting from the desk review and explain the process for obtaining the participants’ consent and any necessary government permissions. A detailed work plan and data quality assessment should be annexed to the report. The main text of the inception report should not exceed 10 pages. The inception report as well as all the suggested tools should be delivered in Arabic& English.

- Analyze results of the research

- Draft the final evaluation study and submit an initial draft

- Incorporate comments, new information, clarifications and additional inputs received upon agreeing to feedback

- Submit a complete final draft to CARE in addition to a short guidance note on how to use the data collection tools, and design a PPT that summarizes the whole process and results as well as conduct the presentation to CARE Egypt staff.

- Final deliverable must be in Arabic and English.

- All original datasets/ raw data and questionnaires used must be handed to CARE by the end of the assignment. For any use of the produced materials/reports/documents, other than for the purpose of the project and CARE, the consultant must receive a formal approval from CARE in writing.

Execution of Assignment:

Consultancy start and end date:   From 26 June 2024 to 30 June 2024

Coordination and Reporting:

The Consultant will report on progress to  the MEAL Officer who shall within 1 working day of receipt notify the Consultant of its decision concerning the documents or reports received, giving reasons should s/he reject the reports or documents, or request amendments.

Conditions of Implementation:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be use in the assignment, including techniques and tools,

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time-frame.

- Financial Proposal:

The financial proposal should include a breakdown of the cost elements to assist in determining the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement

Consultant Professional Service Fees

| Deliverables / Description | Quantity | Unit of measurement | Unit price | Total |
| --- | --- | --- | --- | --- |

Consultant Administrative Costs

| Description | Unit Cost in EGP | Number Days | Amount |
| --- | --- | --- | --- |

Administrative Costs:  Such costs could include transportation, air tickets, lodging, per diem, departure taxes, training logistics, enumerators, interpreters, etc.  Note that per diem and lodging rates will be per CARE Egypt Foundation policy. No reimbursable expense in excess shall be incurred without CARE's prior written approval.  If Vendor travel reimbursement shall be made under this Agreement, then Vendor shall follow CARE's travel policies and be subject to CARE per diem rates

Deadline for sending the technical and financial proposal is 23-06-2024 Financial proposal should include Taxes and other expenses (if any), to be sent to CARE Egypt Foundation – Att. Procurement Officer Name to (Procurement Officer Email), with subject (Final Evaluation / ILO Social enterprise) Any proposals received after the deadline mentioned, will not be considered. Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Please feel free to contact us via email for any further details or inquiry via email prior (24/6/2024)

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money as follows:

| Total | Finance Evaluation | Program Evaluation |  |
| --- | --- | --- | --- |
|  |  |  | Technicality 70%: Qualifications; 10%. Service proposed (Methodology of work and expected results); 30%. Experience (including CV and work history); 9%. Previous experience with CARE; 1%. Time frame and commitment; 20%. Total; 70%. |
|  |  |  | Financial 30%: - Delivery Time - Payment Term - Accuracy of received documents and invoices |

CEF keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments (done within 30-45 working days from invoice submission and linked with deliverables and timeline.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus the financial proposal should include all taxes