Ending Violence against women and girls

- Terms of Reference

Policy analysis mission

CARE Egypt Foundation

CARE Egypt Foundation for Development, registration no 833 for the year 2018,

Insert the program name

"Ending Violence Against Women and Girls - EVAWG"

Insert the initiative name

The project "Ending Violence Against Women and Girls - EVAWG" focuses on ending violence against women and girls (VAWG) in Egypt. The main intervention of the project is centered on improving prevention and response to VAWG. The project commenced in September 2023, funded by USAID Egypt, and will span five years, working in six governorates: Dakahlia, Behaira, Sharkia, Fayoum, Assuit, and Sohag.

Violence Against Women and Girls in Egypt:

Violence against women and girls (VAWG) in Egypt manifests in various forms, including domestic violence, female genital mutilation (FGM), sexual harassment, trafficking in person and child marriage, and online violence. According to a UN Women report, 25.6% of ever-partnered women aged 15-49 years have experienced physical and/or sexual intimate partner violence at least once in their lifetime, with 14% experiencing it in the last 12 months. Although Egypt lacks a specific domestic violence law, most related articles are covered under penalty law.

FGM and sexual harassment remain pressing issues. Despite the ban on FGM since 2008, the practice continues, particularly in rural areas, less wealthy households, and among less educated women and girls. A 2013 United Nations survey indicated that 99.3% of Egyptian women have experienced some form of sexual harassment. Despite the 2014 law criminalizing sexual harassment, many women hesitate to report incidents due to fear of retaliation or social stigma.

Trafficking in person and child marriage, and online violence further exacerbate the situation. child marriage deprives girls of education and exposes them to health risks and domestic violence. Online violence, including cyberbullying and digital harassment, has become increasingly prevalent, posing new challenges to women's safety and well-being in the digital age.

This multifaceted violence against women and girls highlights the urgent need for comprehensive policy analysis and robust interventions to address and mitigate these issues effectively.

Objective of the Assignment:

The purpose of this consultancy is to prepare a comprehensive policy analysis of the current policies, laws, and legal procedures related to all forms of violence against women including domestic violence, Child marriage and trafficking in person, FGM, sexual harassment in Egypt. The policy analysis should also identify gaps in the current legal framework and make recommendations for improvements, highlighting best practices from different countries.

Scope of Work and Deliverables:

The consultant will be responsible to conduct this policy analysis for different form of violence against women and girls including:

  - Domestic violence / intimate partner violence.

  - Female genital mutilation (FGM).

  - Sexual harassment.

  - Child marriage and Trafficking in person.

The consultant is expected to provide his report divided to four different chapters, one for each  form of violence . Each chapter should include:

- literature review for current laws , polices and applications related to the  related to each form of violence against women and girls separately. These forms are:

- Review the legal framework related laws, policies and practices regarding application of these laws and policies .

- Identify gaps in the current legislative framework .

- Develop recommendations needed changes in laws and policies.

- .

Deliverables:

The consultant will be expected to deliver a final approved report including the following:

- A separate chapter for each form of violence as follows: Domestic Violence, FGM, Sexual Harassment, Trafficking in person and child marriage,. Each chapter should include section for the following:

- A literature review for legal framework related to each form of violence in  Middle East and other  .

- A review of the legal framework (laws, policies, and procedures) in Egypt, compared with other countries, especially in the Arab region.

- Identification of gaps in the current laws and polices in Egypt.

- Recommendations for action to address these issues, incorporating best practices from other countries.

To achieve this, the consultant is expected to submit 3 drafts of the policy analysis as follows: a first and a second draft to the program  for review, receive comments, and modify the document before submitting the third and final version.

The policy analysis final version will be submitted in both Arabic and English, with executive summary and  the consultant responsible for translation quality.

Consultant’s Qualifications:

The consultant should have the following qualifications:

- A degree in law is a must.

- Experience conducting similar studies of policy analyses, particularly related to EVAWG.

- Knowledge of the legal framework in Egypt.

- Excellent analytical and writing skills.

Fluency in English and Arabic is preferred

Consultancy Level of Effort

A maximum of (50) working days is foreseen for this assignment including preparation and submission final version of report.

The consultancy is expected to start in September and be completed by the end of December (with a total of 50 working days from the contract signing date). The consultant should complete all deliverables, including the translation of the approved final version of policy analysis, within three months of signing the contract.

It should be a disk review study. The study is not expected to include any field work.

Specific Tasks, Outputs and Time Frame

| Tasks | Outputs | No. Days/ Time Frame |
| --- | --- | --- |
| Submit first draft |  |  |
| Submit second draft |  |  |
| Submit final version |  |  |
| Translate the final |  |  |

Execution of Assignment:

Consultancy start and end date:   From 1  /September  / 2024       to    31  /December  /2024

Coordination and Reporting:

The Consultant will report on progress to  (Vivian Thabet /Chief of Party ) to provide feedback and comments.

Conditions of Implementation:

Interested applicants should submit the following documents in their offers:

- Technical Proposal.

    - A brief statement in understanding of the assignment, and general approach to it.

    - A brief description of the methodology proposed to be use in the assignment.

    - A capabilities statement of the consultant organization and/or brief description of relevant (similar) consultancies that would qualify for this assignment. This statement should be included as a separate annex, in addition to the five-page proposal.

    - Consultant CV

    - It should indicate a complete list of deliverables and a proposed time-frame.

- Financial Proposal:

The financial proposal should include a breakdown of the cost elements to assist in determining the rationale of the given rates.

CARE will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement

Consultant Professional Service Fees

| Deliverables / Description | Quantity | Unit of measurement | Unit price | Total |
| --- | --- | --- | --- | --- |

Deadline for sending the technical and financial proposal is _August 21,2024_______________, Financial proposal should include Taxes , to be sent to CARE Egypt Foundation – Att. Procurement Officer Name to (Procurement Officer Email), with subject (Policy analysis/ Ending Violence against women and girls)

* Any proposals received after the deadline mentioned, will not be considered. Please accept our apology for not giving any exceptions or accepting any justification for late receive.

Please feel free to contact us via email for any further details or inquiry via email prior.

Proposals will be assessed against weighted criteria that include understanding of the task; proposed methodology; previous experience and value for money as follows:

| Finance Evaluation | Program Evaluation | Program Evaluation |  |
| --- | --- | --- | --- |
|  |  |  | Technicality 70%: |
|  |  |  | Financial 30%: - Delivery Time - Payment Term |

CARE Egypt keeps all rights to accept or refuse any offer received without giving reasons.

Technical and financial offer will be discussed upon selection.

Payment Schedule:

All payments (done within 30-45 working days from invoice submission and linked with deliverables and timeline.

CARE Egypt foundation will withhold applicable taxes and deposit the funds with the applicable for tax authorities under this agreement. Thus the financial proposal should include all taxes